## Sheet1
Hyperlink | Task Name | Notes | Resource Names | Work | Duration | Start | Finish | Predecessors | Successors | Workstream | Input Work Products | Output Work Products | Capability | E2 | Roles
| Diagnose Phase |  |  | 0 hrs | 31 days? | Tue 01-01-19 | Mon 18-02-19 | [6 empty] | No
| Establish Guiding Principles | Guiding principles are focused on freeing up capital for investment in growth and preservation of capital |  | 0 hrs | 6 days? | Tue 01-01-19 | Wed 09-01-19 |  | 10 |  |  |  |  | No
| Ensure alignment of the engagement objectives by establishing the following guiding principles: |  |  | 0 hrs | 6 days? | Tue 01-01-19 | Wed 09-01-19 | [6 empty] | No
| Safeguard the core business and protect strategic capabilities and resources in key functional groups |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 |  | 5 |  |  |  |  | No | Cost Reduction Manager
| Focus on non-regrettable, third party spend reduction |  |  | 0 hrs | 1 day? | Wed 02-01-19 | Thu 03-01-19 | 4 | 6 |  |  |  |  | No | Cost Reduction Manager
| Align cost takeout measures to longer-term strategic firm initiatives and ensure a positive customer experience |  |  | 0 hrs | 1 day? | Thu 03-01-19 | Fri 04-01-19 | 5 | 7 |  |  |  |  | No | Cost Reduction Manager
| Execute rapidly to realize quick wins and drive immediate value |  |  | 0 hrs | 1 day? | Fri 04-01-19 | Mon 07-01-19 | 6 | 8 |  |  |  |  | No | Cost Reduction Manager
| Emphasize not just on doing it better or faster, but also taking perspective on “should we be doing it at all, or doing it differently?” |  |  | 0 hrs | 1 day? | Mon 07-01-19 | Tue 08-01-19 | 7 | 9 |  |  |  |  | No | Cost Reduction Manager
| Establish the starting point as baseline for COGS/OPEX and focus on improving run rate cost |  |  | 0 hrs | 1 day? | Tue 08-01-19 | Wed 09-01-19 | 8 | 11 |  |  |  |  | No | Cost Reduction Manager
| Build Team | It is critical to understand who makes up the working team and where accountability resides across the program |  | 0 hrs | 2 days? | Wed 09-01-19 | Fri 11-01-19 | 2 | 13 |  |  |  |  | No
| Understand the team structure |  |  | 0 hrs | 1 day? | Wed 09-01-19 | Thu 10-01-19 | 9 | 12 |  |  |  |  | No | Cost Reduction Manager
| Build RACI |  |  | 0 hrs | 1 day? | Thu 10-01-19 | Fri 11-01-19 | 11 | 14 |  |  | RACI Matrix |  | No | Cost Reduction Manager
| Baseline | Identifying cost drivers help determine focus areas and gaps across functions |  | 0 hrs | 2 days? | Mon 14-01-19 | Wed 16-01-19 | 10 | 16 |  |  |  |  | No
| Understand key cost drivers by function to help identify focus areas and gaps (why costs are higher or lower) and drive actionable outcomes |  |  | 0 hrs | 1 day? | Mon 14-01-19 | Tue 15-01-19 | 12 | 15 |  |  |  |  | No | Cost Reduction Manager
| Review and break down cost drivers into level 1 and level 2 to ensure an exhaustive review of potential opportunities occurs |  |  | 0 hrs | 1 day? | Tue 15-01-19 | Wed 16-01-19 | 14 | 18 |  |  | Cost Driver Framework |  | No | Cost Reduction Manager
| Benchmark | Benchmarking provides a quantitative comparison to baseline and enables realistic target setting |  | 0 hrs | 6 days? | Wed 16-01-19 | Thu 24-01-19 | 13 | 26 |  |  |  |  | No
| Identify peer set |  |  | 0 hrs | 1 day? | Wed 16-01-19 | Thu 17-01-19 | [6 empty] | No
| Identify comparable companies based off sector, industry, revenue, geography, etc. to create customized peer set |  |  | 0 hrs | 1 day? | Wed 16-01-19 | Thu 17-01-19 | 15 | 20 |  |  |  |  | No | Cost Reduction Manager
| Source benchmarking data |  |  | 0 hrs | 1 day? | Thu 17-01-19 | Fri 18-01-19 | [6 empty] | No
| Leverage EY resources (EY Benchmark, APQC, etc.) to source benchmark cost metrics for peer set |  |  | 0 hrs | 1 day? | Thu 17-01-19 | Fri 18-01-19 | 18 | 21 |  |  | Peer Benchmarking Metrics |  | No | Cost Reduction Manager
| Select metrics to compare against baseline calculations |  |  | 0 hrs | 1 day? | Fri 18-01-19 | Mon 21-01-19 | 20 | 23 |  |  |  |  | No | Cost Reduction Manager
| Evaluate benchmarks |  |  | 0 hrs | 2 days? | Mon 21-01-19 | Wed 23-01-19 | [6 empty] | No
| Compare baseline functional cost data to peer set data to understand competitive positioning |  |  | 0 hrs | 1 day? | Mon 21-01-19 | Tue 22-01-19 | 21 | 24 |  |  |  |  | No | Cost Reduction Manager
| Identify areas where client falls in lower quartiles relative to peers as opportunities for cost takeout |  |  | 0 hrs | 1 day? | Tue 22-01-19 | Wed 23-01-19 | 23 | 25 |  |  |  |  | No | Cost Reduction Manager
| Confirm findings with management and functional leads |  |  | 0 hrs | 1 day? | Wed 23-01-19 | Thu 24-01-19 | 24 | 27 |  |  | List of KPIs |  | No | Cost Reduction Manager
| Set Targets | Target setting outlines the steps involved in setting realistic and achievable targets |  | 0 hrs | 5 days? | Fri 25-01-19 | Fri 01-02-19 | 16 | 32 |  |  |  |  | No
| Compare baseline and benchmark analysis to identify cost gaps |  |  | 0 hrs | 1 day? | Fri 25-01-19 | Mon 28-01-19 | 25 | 28 |  |  |  |  | No | Cost Reduction Manager
| Conduct interviews with stakeholders to validate assumptions and analysis |  |  | 0 hrs | 1 day? | Mon 28-01-19 | Tue 29-01-19 | 27 | 29 |  |  |  |  | No | Cost Reduction Manager
| Formulate high level hypothesis for range based estimates of potential savings from gaps identified |  |  | 0 hrs | 1 day? | Tue 29-01-19 | Wed 30-01-19 | 28 | 30 |  |  |  |  | No | Cost Reduction Manager
| Develop savings hypotheses at the functional level |  |  | 0 hrs | 1 day? | Wed 30-01-19 | Thu 31-01-19 | 29 | 31 |  |  | Saving Hypothesis |  | No | Cost Reduction Manager
| Validate target savings hypotheses |  |  | 0 hrs | 1 day? | Thu 31-01-19 | Fri 01-02-19 | 30 | 33 |  |  |  |  | No | Cost Reduction Manager
| Perform Budgeting | Embedding cost reduction initiatives in budgets helps to eliminate continuous manual monitoring of cost savings initiatives |  | 0 hrs | 9 days? | Fri 01-02-19 | Fri 15-02-19 | 26 | 44 |  |  |  |  | No
| Review historical and current budgets to establish a baseline and understand capital allocations |  |  | 0 hrs | 1 day? | Fri 01-02-19 | Mon 04-02-19 | 31 | 34 |  |  | Holistic Budget |  | No | Cost Reduction Manager
| Set a connect between COO/CSCO and sub-functional leaders to catalogue all selected cost reduction levers/initiatives at the functional and enterprise levels |  |  | 0 hrs | 1 day? | Mon 04-02-19 | Tue 05-02-19 | 33 | 36 |  |  |  |  | No | Cost Reduction Manager
| Provide a consolidated list to the finance department for budget revisioning: |  |  | 0 hrs | 3 days? | Tue 05-02-19 | Mon 11-02-19 | [6 empty] | No
| Identify initiatives that will impact each individual function and map cost savings targets to cost centres as identified in the budget |  |  | 0 hrs | 1 day? | Tue 05-02-19 | Wed 06-02-19 | 34 | 37 |  |  |  |  | No | Cost Reduction Manager
| Allocate costs savings to individual functional cost centres and forecast a new run rate |  |  | 0 hrs | 1 day? | Thu 07-02-19 | Fri 08-02-19 | 36 | 38 |  |  |  |  | No | Cost Reduction Manager
| Stage savings on a monthly or quarterly basis to increase tracking accuracy |  |  | 0 hrs | 1 day? | Fri 08-02-19 | Mon 11-02-19 | 37 | 39 |  |  |  |  | No | Cost Reduction Manager
| Continue to track progress of initiatives against budget targets |  |  | 0 hrs | 1 day? | Mon 11-02-19 | Tue 12-02-19 | 38 | 41 |  |  |  |  | No | Cost Reduction Manager
| Conduct pressure test to ensure validity |  |  | 0 hrs | 3 days? | Tue 12-02-19 | Fri 15-02-19 | [6 empty] | No
| Challenge assumptions and pressure-test ideas to validate opportunities |  |  | 0 hrs | 1 day? | Tue 12-02-19 | Wed 13-02-19 | 39 | 42 |  |  |  |  | No | Cost Reduction Manager
| Review required functional inputs and cross-functional handoffs |  |  | 0 hrs | 1 day? | Wed 13-02-19 | Thu 14-02-19 | 41 | 43 |  |  |  |  | No | Cost Reduction Manager
| Confirm that costs are eliminated, not shifted to other functional groups |  |  | 0 hrs | 1 day? | Thu 14-02-19 | Fri 15-02-19 | 42 | 45 |  |  |  |  | No | Cost Reduction Manager
| Build Roadmap | Implementing activities in line with the roadmap defined helps win client confidence and facilitates driving the engagement |  | 0 hrs | 1 day? | Fri 15-02-19 | Mon 18-02-19 | 32 | 47 |  |  |  |  | No
| Prepare an implementation roadmap with detailed activities and timelines for the management |  |  | 0 hrs | 1 day? | Fri 15-02-19 | Mon 18-02-19 | 43 | 49 |  |  | Implementation Roadmap |  | No | Cost Reduction Manager
| Implement Phase |  |  | 0 hrs | 42 days? | Mon 18-02-19 | Thu 25-04-19 | [6 empty] | No
| Conduct Workshops | Strategic planning workshops help develop a clear path to executing RCT program initiatives |  | 0 hrs | 7 days? | Mon 18-02-19 | Thu 28-02-19 | 44 | 57 |  |  |  |  | No
| Conduct explanatory workshop to validate current state baseline assessment, evaluate competitive positioning and align on company specific priority cost reduction goals |  |  | 0 hrs | 4 days? | Mon 18-02-19 | Mon 25-02-19 |  |  |  |  | Agreed upon baseline cost and organization |  | No
| Review non-personnel spend with functional leads |  |  | 0 hrs | 1 day? | Mon 18-02-19 | Tue 19-02-19 | 45 | 50 |  |  |  |  | No | Cost Reduction Manager
| Present functional industry benchmarking |  |  | 0 hrs | 1 day? | Wed 20-02-19 | Thu 21-02-19 | 49 | 51 |  |  |  |  | No | Cost Reduction Manager
| Ideate on cost reduction hypotheses |  |  | 0 hrs | 1 day? | Thu 21-02-19 | Fri 22-02-19 | 50 | 52 |  |  | List of cost reduction hypotheses |  | No | Cost Reduction Manager
| Design prioritization framework |  |  | 0 hrs | 1 day? | Fri 22-02-19 | Mon 25-02-19 | 51 | 54 |  |  |  |  | No | Cost Reduction Manager
| Conduct design workshop to ensure targeted cost reduction goals are feasible and to validate timing |  |  | 0 hrs | 3 days? | Mon 25-02-19 | Thu 28-02-19 |  |  |  |  | Future state operating model, Future roadmap |  | No
| Present cost reduction initiatives |  |  | 0 hrs | 1 day? | Mon 25-02-19 | Tue 26-02-19 | 52 | 55 |  |  |  |  | No | Cost Reduction Manager
| Identify one-time costs and risks associated with each cost reduction initiative |  |  | 0 hrs | 1 day? | Tue 26-02-19 | Wed 27-02-19 | 54 | 56 |  |  |  |  | No | Cost Reduction Manager
| Prioritize execution of initiatives based on feasibility and overall value opportunity |  |  | 0 hrs | 1 day? | Wed 27-02-19 | Thu 28-02-19 | 55 | 58 |  |  |  |  | No | Cost Reduction Manager
| Undertake cost takeout initiatives | Identifying levers that drive rapid cost takeout help optimize margin performance |  | 0 hrs | 1 day? | Thu 28-02-19 | Fri 01-03-19 | 47 | 59 |  |  |  |  | No
| Define cost takeout initiatives to facilitate choosing areas and levers that need to be focused on during the course of the engagement | There are four broader categories of levers which have different timeline of impact: Plan, Source, Make, Deliver |  | 0 hrs | 1 day? | Thu 28-02-19 | Fri 01-03-19 | 56 | 60 |  |  |  |  | No | Cost Reduction Manager
| Prioritize | Prioritize value creation projects and develop plans with near-term actions and longer-term initiatives |  | 0 hrs | 7 days? | Fri 01-03-19 | Wed 13-03-19 | 57 | 68 |  |  |  |  | No
| Select and prioritize key cost reduction areas to develop the initiative implementation timeline and roadmap |  |  | 0 hrs | 1 day? | Fri 01-03-19 | Mon 04-03-19 | 58 | 62 |  |  | Prioritization Matrix |  | No | Cost Reduction Manager
| Develop a clear plan and supporting initiatives for moving forward with the agreed-to portfolio of cost improvement initiatives |  |  | 0 hrs | 5 days? | Tue 05-03-19 | Tue 12-03-19 | [6 empty] | No
| Build a list of milestones for each cost reduction initiative and identify the priority level |  |  | 0 hrs | 1 day? | Tue 05-03-19 | Wed 06-03-19 | 60 | 63 |  |  |  |  | No | Cost Reduction Manager
| Break down each milestone into a list of actionable tasks |  |  | 0 hrs | 1 day? | Wed 06-03-19 | Thu 07-03-19 | 62 | 64 |  |  |  |  | No | Cost Reduction Manager
| Determine the start/end date for each initiative and assign owners for implementation |  |  | 0 hrs | 1 day? | Thu 07-03-19 | Fri 08-03-19 | 63 | 65 |  |  |  |  | No | Cost Reduction Manager
| Highlight interdependencies to build a critical path |  |  | 0 hrs | 1 day? | Fri 08-03-19 | Mon 11-03-19 | 64 | 66 |  |  |  |  | No | Cost Reduction Manager
| Plot the tasks on a timeline to provide a project road map |  |  | 0 hrs | 1 day? | Mon 11-03-19 | Tue 12-03-19 | 65 | 67 |  |  |  |  | No | Cost Reduction Manager
| Develop an integrated roadmap for implementation, including a phased execution approach to implement cost reduction initiatives |  |  | 0 hrs | 1 day? | Tue 12-03-19 | Wed 13-03-19 | 66 | 69 |  |  | Implementation Roadmap |  | No | Cost Reduction Manager
| Determine Program Structure | Clear accountability and governance are critical for the success of a program |  | 0 hrs | 4 days? | Wed 13-03-19 | Wed 20-03-19 | 59 | 73 |  |  |  |  | No
| Define the structure of the engagement with clear roles and responsibilities |  |  | 0 hrs | 1 day? | Wed 13-03-19 | Thu 14-03-19 | 67 | 70 |  |  | Program Structure |  | No | Cost Reduction Manager
| Define the decision acceleration and escalation process or matrix |  |  | 0 hrs | 1 day? | Thu 14-03-19 | Fri 15-03-19 | 69 | 71 |  |  | Key decision acceleration and escalation process |  | No | Cost Reduction Manager
| Set up a weekly cadence to ensure consistency and accountability |  |  | 0 hrs | 1 day? | Mon 18-03-19 | Tue 19-03-19 | 70 | 72 |  |  |  |  | No | Cost Reduction Manager
| Launch quick wins and no-regret actions to build momentum and establish governance, accountability and consistency for longer-term value realization |  |  | 0 hrs | 1 day? | Tue 19-03-19 | Wed 20-03-19 | 71 | 75 |  |  |  |  | No | Cost Reduction Manager
| Communicate | Having a comprehensive understanding of firm culture will inform communications approach and help anticipate risks to morale |  | 0 hrs | 6 days? | Wed 20-03-19 | Thu 28-03-19 | 68 | 81 |  |  |  |  | No
| Consider culture when executing cost takeout |  |  | 0 hrs | 3 days? | Wed 20-03-19 | Mon 25-03-19 | [6 empty] | No
| Conduct Culture Fitness Diagnostic to understand current culture, desired culture and how to support employees through a shift |  |  | 0 hrs | 1 day? | Wed 20-03-19 | Thu 21-03-19 | 72 | 76 |  |  |  |  | No | Cost Reduction Manager
| Define and align on desired go-forward cultural blueprint and begin promoting those values in communications |  |  | 0 hrs | 1 day? | Thu 21-03-19 | Fri 22-03-19 | 75 | 77 |  |  |  |  | No | Cost Reduction Manager
| Anticipate potential impact to morale from takeout initiatives and develop communications plans to mitigate risks |  |  | 0 hrs | 1 day? | Fri 22-03-19 | Mon 25-03-19 | 76 | 78 |  |  |  |  | No | Cost Reduction Manager
| Develop a structured communications and change management program |  |  | 0 hrs | 1 day? | Mon 25-03-19 | Tue 26-03-19 | 77 | 79 |  |  | Communication Plan, Change Management Plan |  | No | Cost Reduction Manager
| Structure the transformation and communications program |  |  | 0 hrs | 1 day? | Tue 26-03-19 | Wed 27-03-19 | 78 | 80 |  |  |  |  | No | Cost Reduction Manager
| Develop a comprehensive communication plan to inform stakeholders of changes |  |  | 0 hrs | 1 day? | Wed 27-03-19 | Thu 28-03-19 | 79 | 82 |  |  |  |  | No | Cost Reduction Manager
| Track and Realize | Centralized tracking of value-capture initiatives |  | 0 hrs | 12 days? | Fri 29-03-19 | Wed 17-04-19 | 73 | 97 |  |  |  |  | No
| For each of the selected cost reduction initiatives, develop an initiative charter |  |  | 0 hrs | 1 day? | Fri 29-03-19 | Mon 01-04-19 | 80 | 84 |  |  | Charter |  | No | Cost Reduction Manager
| Establish tracking process |  |  | 0 hrs | 4 days? | Mon 01-04-19 | Fri 05-04-19 | [6 empty] | No
| Align on program tools and templates to be leveraged for tracking |  |  | 0 hrs | 1 day? | Mon 01-04-19 | Tue 02-04-19 | 82 | 85 |  |  |  |  | No | Cost Reduction Manager
| Establish the approach, frequency and reporting |  |  | 0 hrs | 1 day? | Tue 02-04-19 | Wed 03-04-19 | 84 | 86 |  |  |  |  | No | Cost Reduction Manager
| Distribute finalized value creation targets/timelines to functional teams |  |  | 0 hrs | 1 day? | Wed 03-04-19 | Thu 04-04-19 | 85 | 87 |  |  |  |  | No | Cost Reduction Manager
| Train stakeholders on the tracking approach and project tools |  |  | 0 hrs | 1 day? | Thu 04-04-19 | Fri 05-04-19 | 86 | 89 |  |  |  |  | No | Cost Reduction Manager
| Track and measure initiatives. Each functional team to regularly track the progress of cost takeout activities: |  |  | 0 hrs | 5 days? | Fri 05-04-19 | Mon 15-04-19 | [6 empty] | No
| Operational progress toward value creation milestones |  |  | 0 hrs | 1 day? | Fri 05-04-19 | Mon 08-04-19 | 87 | 90 |  |  |  |  | No | Cost Reduction Manager
| Achieved and incremental value |  |  | 0 hrs | 1 day? | Mon 08-04-19 | Tue 09-04-19 | 89 | 91 |  |  |  |  | No | Cost Reduction Manager
| One-time costs and incurred Capex |  |  | 0 hrs | 1 day? | Tue 09-04-19 | Wed 10-04-19 | 90 | 92 |  |  |  |  | No | Cost Reduction Manager
| Net value across effected teams |  |  | 0 hrs | 1 day? | Thu 11-04-19 | Fri 12-04-19 | 91 | 93 |  |  |  |  | No | Cost Reduction Manager
| Relevant KPIs |  |  | 0 hrs | 1 day? | Fri 12-04-19 | Mon 15-04-19 | 92 | 95 |  |  |  |  | No | Cost Reduction Manager
| Review and Report Progress |  |  | 0 hrs | 2 days? | Mon 15-04-19 | Wed 17-04-19 |  |  |  |  | Status Report |  | No
| Regularly compare outcomes achieved vs. forecasted for each initiative |  |  | 0 hrs | 1 day? | Mon 15-04-19 | Tue 16-04-19 | 93 | 96 |  |  |  |  | No | Cost Reduction Manager
| Address identified progress challenges, dependencies and risks |  |  | 0 hrs | 1 day? | Tue 16-04-19 | Wed 17-04-19 | 95 | 98 |  |  |  |  | No | Cost Reduction Manager
| Review and Learn | Capturing real-time lessons learned and synthesizing stakeholder feedback via surveys is key for documenting lessons learned |  | 0 hrs | 5 days? | Wed 17-04-19 | Thu 25-04-19 | 81 | [5 empty] | No
| Capture real-time lessons learned and document findings in a best practices log throughout the program |  |  | 0 hrs | 1 day? | Wed 17-04-19 | Thu 18-04-19 | 96 | 100 |  |  |  |  | No | Cost Reduction Manager
| Conduct stakeholder surveys |  |  | 0 hrs | 2 days? | Thu 18-04-19 | Mon 22-04-19 | [6 empty] | No
| Use survey results to identify variances against original strategic objectives and process deficiencies |  |  | 0 hrs | 1 day? | Thu 18-04-19 | Fri 19-04-19 | 98 | 101 |  |  |  |  | No | Cost Reduction Manager
| Use results to enable a mid-program course correction to get back on track if necessary |  |  | 0 hrs | 1 day? | Fri 19-04-19 | Mon 22-04-19 | 100 | 102 |  |  |  |  | No | Cost Reduction Manager
| Conduct a lessons-learned workshop |  |  | 0 hrs | 1 day? | Mon 22-04-19 | Tue 23-04-19 | 101 | 103 |  |  |  |  | No | Cost Reduction Manager
| Conduct a debrief meeting with steering committee |  |  | 0 hrs | 1 day? | Wed 24-04-19 | Thu 25-04-19 | 102 | [5 empty] | No | Cost Reduction Manager
| Project Management |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Start up and Prepare the Project |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Conduct project kickoff |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Establish project charter |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Develop project schedule |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Identify issues and risks |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Manage Project Delivery |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Report status |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Direct and manage project work |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Control costs |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Manage and issue risks |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Manage project changes |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Perform quality assurance |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Close the project |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No
| Close project or phase |  |  | 0 hrs | 1 day? | Tue 01-01-19 | Wed 02-01-19 | [6 empty] | No