## Plan
WBS | Hyperlink | Task Name | Resource Names | Notes | Duration | Work | Start | Finish | Predecessors
1 |  | Transportation and Warehousing Loss Review |  | Use this project plan as a starting point to plan and execute the engagement.The project manager will have to use a combination of his/her own experience, other methods, project planning skills, and the specific requirements of the project stakeholders... | 31 days | 114.75 hrs | Mon 2/4/19 | Fri 3/22/19
1.1 |  | Conduct Interviews and Warehouse Site Visits |  | Interviews with stakeholders, clients, and suppliers. Repeat as needed | 8 days | 0 hrs | Mon 2/4/19 | Thu 2/14/19
1.1.1 |  | Prepare for interviews |  |  | 3 days | 0 hrs | Mon 2/4/19 | Thu 2/7/19
1.1.2 |  | Conduct interviews |  |  | 1 day | 0 hrs | Mon 2/4/19 | Tue 2/5/19
1.1.3 |  | Summarize interviews |  |  | 1 day | 0 hrs | Mon 2/4/19 | Tue 2/5/19
1.2 | https://methods.ey.com/Production/optimize/#process.adv.ent_assess_optimize_lifecycle.base/capabilitypatterns/analyze_bus_cap_D1190E73.html?proc=_b8T6wBQgEemAi-AGVplqLQ&path=_b8T6wBQgEemAi-AGVplqLQ,_ayRlYL9aEem07M-EqYlUXg,_UFQI0d7MEem7pch6RTlhog | Assess Organization, Processes, IT / Technology |  | Iterate as needed | 18 days | 0 hrs | Mon 2/4/19 | Mon 3/4/19 | 2
1.2.1 |  | Analyze people dimension |  | Assess co-packers and contracts (use-case, strategy, performance, commercials, incentives). | 1 day? | 0 hrs | Mon 2/4/19 | Tue 2/5/19
1.2.2 |  | Assess process dimension |  | Assess process, IT and opps for automation and for external collaboration | 1 day? | 0 hrs | Mon 2/4/19 | Tue 2/5/19
1.2.3 |  | Assess organization dimension |  | Assess organization and headcount (internal and external) | 1 day? | 0 hrs | Mon 2/4/19 | Tue 2/5/19
1.2.4 |  | Assess multi-modals (technology enablement) |  | Assess multi-modals opportunities... | 1 day? | 0 hrs | Mon 2/4/19 | Tue 2/5/19
1.2.5 |  | Develop first draft of cost savings opportunities |  |  | 10 days | 0 hrs | Mon 2/4/19 | Tue 2/19/19
1.3 | https://methods.ey.com/Production/optimize/#process.adv.ent_assess_optimize_lifecycle.base/capabilitypatterns/estab_curr_st_perf_base_info_F088553E.html?proc=_b8T6wBQgEemAi-AGVplqLQ&path=_b8T6wBQgEemAi-AGVplqLQ,_ayRlYL9aEem07M-EqYlUXg,_dgaMwS7lEemuovPhlwz | Analyze Transportation and Warehousing Data (Performance Measurement) |  |  | 10 days | 0 hrs | Mon 2/4/19 | Tue 2/19/19
1.3.1 |  | Create data request |  |  | 2 days | 0 hrs | Mon 2/4/19 | Wed 2/6/19
1.3.2 |  | Develop initial data-driven insights and observations |  |  | 10 days | 0 hrs | Mon 2/4/19 | Tue 2/19/19
1.3.3 |  | Cleanse and refine data |  |  | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.3.4 |  | Develop analytic reports |  | Smart Maps, trade analytics, headcount analysis | 10 days | 0 hrs | Mon 2/4/19 | Tue 2/19/19
1.3.5 |  | Refine data-driven observations |  |  | 10 days | 0 hrs | Mon 2/4/19 | Tue 2/19/19
1.4 | https://methods.ey.com/Production/optimize/#process.adv.ent_assess_optimize_lifecycle.base/capabilitypatterns/eval_baseline_against_obj_measures_6BA4B4E3.html?proc=_b8T6wBQgEemAi-AGVplqLQ&path=_b8T6wBQgEemAi-AGVplqLQ,_ayRlYL9aEem07M-EqYlUXg,__P2-YS7vEemuo | Evaluate Baseline Against Benchmarks and Leading Practices |  |  | 15 days | 0 hrs | Mon 2/4/19 | Tue 2/26/19
1.4.1 |  | Compare against benchmarks |  |  | 15 days | 0 hrs | Mon 2/4/19 | Tue 2/26/19
1.4.2 |  | Compare against leading practices |  |  | 10 days | 0 hrs | Mon 2/4/19 | Tue 2/19/19
1.4.3 |  | Compare against peer discussions |  |  | 10 days | 0 hrs | Mon 2/4/19 | Tue 2/19/19
1.5 |  | Create Transportation and Warehouse Loss Review Analysis Playbook |  |  | 15 days | 0 hrs | Mon 2/4/19 | Tue 2/26/19
1.5.1 |  | Assess and document ongoing initiatives |  | ... | 15 days | 0 hrs | Mon 2/4/19 | Tue 2/26/19
1.5.2 |  | Prepare playbook |  |  | 15 days | 0 hrs | Mon 2/4/19 | Tue 2/26/19
1.6 | https://methods.ey.com/Production/optimize/#process.adv.optimize.base/deliveryprocesses/dev_bus_case_506BA928.html?proc=_b8T6wBQgEemAi-AGVplqLQ&path=_b8T6wBQgEemAi-AGVplqLQ,_DHXJcC-2Eeme_MgwgEXHLw,_lKqHAeqzEemvWuFOl07P8Q | Develop high-level business case |  |  | 10 days | 0 hrs | Mon 3/4/19 | Tue 3/19/19 | 6
1.7 | https://methods.ey.com/Production/optimize/#process.adv.ent_assess_optimize_lifecycle.base/capabilitypatterns/id_set_improv_opps_agnst_ref_model_88109DA2.html?proc=_b8T6wBQgEemAi-AGVplqLQ&path=_b8T6wBQgEemAi-AGVplqLQ,_ayRlYL9aEem07M-EqYlUXg,_afFIwS7wEemuo | Prioritize opportunities |  |  | 10 days | 0 hrs | Mon 3/4/19 | Tue 3/19/19 | 6
1.8 | https://methods.ey.com/Production/optimize/#process.adv.optimize.base/deliveryprocesses/dev_init_portfolio_rdmp_AFA6CB59.html?proc=_b8T6wBQgEemAi-AGVplqLQ&path=_b8T6wBQgEemAi-AGVplqLQ,_DHXJcC-2Eeme_MgwgEXHLw,_hcsAceqzEemvWuFOl07P8Q | Develop roadmap |  |  | 10 days | 0 hrs | Mon 3/4/19 | Tue 3/19/19 | 6
1.9 |  | Conduct Report Out Session |  |  | 31 days | 0 hrs | Mon 2/4/19 | Fri 3/22/19
1.9.1 |  | Prepare materials for meeting |  |  | 3 days | 0 hrs | Tue 3/19/19 | Fri 3/22/19 | 12,13,14,15,21,25
1.9.2 |  | Conduct meeting session |  |  | 1 day | 0 hrs | Mon 2/4/19 | Tue 2/5/19
1.9.3 |  | Prepare and distribute meeting results |  |  | 1 day | 0 hrs | Mon 2/4/19 | Tue 2/5/19
1.1 | https://methods.ey.com/production/optimize/#process.adv.optimize.base/deliveryprocesses/manage_proj_2F9AAA57.html | Manage the Project |  |  | 15 days | 114.75 hrs | Mon 2/4/19 | Tue 2/26/19
1.10.1 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.assign/capabilitypatterns/initiate_proj_E945A9CB.html | Initiate the Project |  | Define a new project or a new phase of an existing project by obtaining authorization to start the project or phase. | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.2 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/identify_stakeholders_B25AA8F0.html | Identify stakeholders |  | Identify stakeholders that will be impacted or need to be engaged to meet the program objectives | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.3 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/define_scope_F123D016.html | Define scope |  | Develop a detailed description of the relevant area or subject matter that the project will encompass. | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.4 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/create_wbs_EEE421F8.html | Create work breakdown structure |  | Develop a deliverable-oriented, hierarchical decomposition of all the work that must be performed in order to accomplish the objectives of a project. | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.5 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/estimate_project_work_effort_B572423.html | Estimate project work effort |  | Approximation of the total effort (measured in hour, days, etc) that it will take to complete all proposed tasks. &#xD;... | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.1.5 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/estimate_costs_E9BF49E2.html | Estimate costs |  | The required amount of resource and costs that will be needed to complete all of the necessary work. | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.1.6 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_mini.base/tasks/develop_schedule_44BF7AB6.html | Develop project schedule |  | Analyze activity sequences, durations, resource allocations, business constraints and dependencies and create a work plan. | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.1.7 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/identify_risks_85804E2.html | Identify risks |  | Determine future events which may adversely affect the project and document their characteristics. | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.1.8 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/est_proj_mgt_office_C20FAFE.html | Establish project management office |  | Establish the group or department that defines and maintains project management standards and protocols for the project. | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.1.9 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/acquire_project_team_DB0AB409.html | Acquire project team |  | Assemble the team competencies and roles necessary to complete project activities. | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.1.10 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_mini.base/tasks/establish_proj_charter_CEC70964.html | Establish project charter |  | Leverage the existing information and project background materials to summarize the key information in the charter. | 5 days | 0 hrs | Mon 2/4/19 | Mon 2/11/19
1.10.2 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.assign/capabilitypatterns/plan_proj_FBFAE0FF.html | Plan the Project and Conduct Team Kickoff |  | Establish the scope of the project, refine the objectives, and define the course of action required to attain the objectives that the project is undertaken to achieve. | 10 days | 0 hrs | Mon 2/11/19 | Tue 2/26/19 | 33
1.10.2.1 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.assign/capabilitypatterns/plan_scope_757D69DF.html | Plan Scope |  | Describes the relevant area or subject matter that the project will encompass. | 10 days | 0 hrs | Mon 2/11/19 | Tue 2/26/19
1.10.2.1.1 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/define_scope_F123D016.html | Define scope |  | Develop a detailed description of the relevant area or subject matter that the project will encompass. | 10 days | 0 hrs | Mon 2/11/19 | Tue 2/26/19
1.10.2.1.2 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/create_wbs_EEE421F8.html | Create work breakdown structure |  | Develop a deliverable-oriented, hierarchical decomposition of all the work that must be performed in order to accomplish the objectives of a project. | 10 days | 0 hrs | Mon 2/11/19 | Tue 2/26/19
1.10.2.2 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.assign/capabilitypatterns/plan_schedule_449F6F25.html | Plan Schedule |  | Define the course of action required to attain the objectives that the project is undertaken to achieve. | 10 days | 0 hrs | Mon 2/11/19 | Tue 2/26/19
1.10.2.2.1 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_mini.base/tasks/develop_schedule_44BF7AB6.html | Develop project schedule |  | Analyze activity sequences, durations, resource allocations, business constraints and dependencies and create a work plan. Refine category work plan. Finalize key performance indicators, and delivery milestones.... | 10 days | 0 hrs | Mon 2/11/19 | Tue 2/26/19
1.10.2.2.2 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/establish_project_baseline_ADF58119.html | Establish project baseline |  | Initiate the accepted and approved management plan for a project. | 10 days | 0 hrs | Mon 2/11/19 | Tue 2/26/19
1.10.2.3 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.assign/capabilitypatterns/plan_cost_E7F3ABB4.html | Plan Cost |  | Establish the policies, procedures, and documentation for planning, managing, expending, and controlling project costs. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.3.1 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/plan_cost_management_FFB5D6C6.html | Plan cost management |  | Establish the policies, procedures, and documentation for planning, managing, expending, and controlling project costs. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.3.2 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/estimate_costs_E9BF49E2.html | Estimate costs |  | The required amount of resource and costs that will be needed to complete all of the necessary work. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.3.3 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/confirm_cost_baseline_2BF1827F.html | Confirm cost baseline |  | Aggregate the estimated costs of individual activities or work packages to establish an authorized cost baseline. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.4 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/plan_quality_management_D6285844.html | Plan quality management |  | Identify excellence standards for the project and its deliverables and document how the project will demonstrate compliance with quality requirements. Finalize agreed reporting templates, and other relevant criteria | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.5 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/plan_hr_mgmt_BA8A5DEA.html | Plan human resource management |  | Identify and document project roles, responsibilities, required skills, reporting relationships, and create a staffing management plan. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.6 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/plan_communications_management_BA821FA6.html | Plan communications management |  | Develop an appropriate approach and plan for project communications based on stakeholderâ€™s information needs, requirements and available organizational assets. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.7 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/develop_proj_kickoff_material_6674431B.html | Develop project kickoff material |  | Prepare the appropriate documents required for formal start of the project. Confirm cross functional category team members and schedule kick-off... | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.8 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_mini.base/tasks/conduct_project_kickoff_9B8E2B84.html | Conduct project kickoff |  | Initiate the formal start of project execution generally though a meeting involving the client and project team. Hold category team kick-off | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.9 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.assign/capabilitypatterns/plan_risk_6AFF4F1D.html | Plan Risk |  | Establish how future events with potential impact to the project will be managed, who will be responsible, and how risk will be communicated throughout the project. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.9.1 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/plan_risk_management_32287FB3.html | Plan risk management |  | Define how risk management activities will be conducted including determination of risk response strategies and tactics that will be used. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.9.2 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/identify_issues_AE53A1FC.html | Identify issues |  | Determine matters that are affecting project progress and that require formal resolution. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.10 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/plan_supplier_management_77A4F978.html | Plan supplier management |  | Document project procurement decisions, specifying the approach, and identify potential suppliers. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.11 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/plan_stakeholder_management_5050BC02.html | Plan stakeholder management |  | Develop strategies to effectively engage stakeholders throughout the project, based on the analysis of their needs, interests, and potential impact on project success. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.12 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/define_chng_mgmt_proc_9E249468.html | Define change management procedures |  | Establish the overall process for how both technical changes and changes in scope will be handled. This includes defining the overall workflow and states for managing changes requests. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.13 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/est_proj_governance_51E78C33.html | Establish project governance structure |  | Assemble the framework of individuals and organizational units within which a project is defined, and to whom a project manager is accountable. This body controls the project and approves deliverables. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.2.14 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/establish_chng_ctrl_board_94BD734C.html | Establish Change Control Board |  | Make sure the required change management boards are established with proper representation. | 5 days | 0 hrs | Mon 2/11/19 | Tue 2/19/19
1.10.3 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.assign/capabilitypatterns/execute_proj_E3641394.html | Execute the Project |  | Deliver the work defined in the project management plan to satisfy the project specifications. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19 | 44
1.10.3.1 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/est_proj_proc_and_standards_1747D1D8.html | Establish project standards and procedures |  | Define and document operational efficiency protocols and processes for the project. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.2 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/direct_project_work_C274174D.html | Direct and manage project work |  | Conduct activities defined in the scheduled and management plan and implement approved changes to achieve the projectâ€™s objectives. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.3 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_mini.base/tasks/perform_quality_assurance_CC581A99.html | Perform quality assurance |  | Audit project level quality requirements and the results from quality control measurements to verify that appropriate quality standards and operational definitions are used. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.4 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/develop_project_team_6F3FEB39.html | Develop project team |  | Improve competencies, team member interaction, and overall team environment to enhance project performance. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.5 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/manage_project_team_A59EAF57.html | Manage project team |  | Track team member performance, providing feedback, resolving issues, and managing changes to optimize project performance. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.6 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_mini.base/tasks/report_status_E94C9963.html | Report status |  | Communicate work progress and status to targeted audiences. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.7 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/manage_communications_19D7A23.html | Manage communications |  | Create, collect, distribute, store, retrieve and track disposition of project information in accordance with the communications management plan. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.8 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/obtain_proj_feedback_569E55DF.html | Obtain project feedback from sponsor |  | Solicit feedback on the quality and usefulness of deliverables and on areas for improvement. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.9 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/obtain_suppliers_E7C66D2.html | Obtain suppliers |  | Select suppliers, and award contracts. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.10 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/respond_to_risks_721085E.html | Respond to risks |  | Implement risk response plan to mitigate future impact to project. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.11 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/act_upon_issues_61025E5E.html | Act upon issues |  | Implement action plan to resolve a project issue. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.3.12 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/plan_next_phase_C8736010.html | Plan next project phase |  | Identify and preliminarily plan for one or more follow-on phases or sub-projects. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.assign/capabilitypatterns/monitor_ctrl_proj_A0A017C6.html | Monitor and Control the Project |  | Track, review, and regulate the progress and performance of the project; identify any areas in which changes to the plan are required; and initiate the corresponding changes. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19 | 44
1.10.4.1 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/validate_scope_AB6B174B.html | Validate scope |  | Formalize acceptance criteria of completed deliverables. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.2 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/control_scope_C610B401.html | Control scope |  | Monitor the status of the project and product scope and manage changes to the scope baseline. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.3 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/control_costs_A2C2B497.html | Control costs |  | Monitor project costs and manage changes to the cost baseline. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.4 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/perform_schedule_control_42C5F2D3.html | Perform schedule control meetings |  | Track, review, and report the progress to meet performance objectives. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.5 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/control_quality_41DC4816.html | Control quality |  | Monitor and record results of executing the quality activities to assess performance and recommend necessary changes. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.6 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/control_communications_49819E21.html | Control communications |  | Monitor communications during the project to verify the information needs of the project stakeholders are met. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.7 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/control_risks_60D7447.html | Control risks |  | Track identified risks, monitor residual risks and evaluate risk process effectiveness throughout the project. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.8 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/control_issues_7875E755.html | Control issues |  | Track identified issues and evaluate issue management process effectiveness throughout the project. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.9 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/manage_suppliers_191A46E2.html | Manage suppliers |  | Control supplier relationships, monitor contract performance, and make changes and corrections as appropriate. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.10 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/manage_stakeholder_engagement_CD298607.html | Manage stakeholder engagement |  | Communicate and work with stakeholders to meet their needs and expectations, address issues as they occur, and develop appropriate stakeholder engagement in project activities. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.11 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/log_change_request_C386FA9B.html | Log change request |  | Request a change following the established change management procedures. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.12 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/assess_route_change_requests_880C6E37.html | Assess and route change requests |  | Perform an initial analysis on submitted changes requests and assign them to the appropriate change control board. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.4.13 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/track_changes_C43F2180.html | Track changes |  | Monitor the change log of any new changes and keep track of the status of existing changes. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.5 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.assign/capabilitypatterns/close_proj_18498FDE.html | Close the Project |  | Finalize all activities across all areas to formally close the project or phase. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19 | 81,68
1.10.5.1 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_med.base/tasks/close_supplier_arrangement_20C3EF4E.html | Close supplier arrangement |  | Complete each project supplier contract or agreement. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.5.2 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_small.base/tasks/conduct_proj_team_debrief_rel_res_F66EB34.html | Conduct project team debrief and release resources |  | Meet with team members to solicit feedback on project performance and end their active participation on the project. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19
1.10.5.3 | https://methods.ey.com/production/optimize/#practice.mgmt.proj.pm_mini.base/tasks/close_project_or_phase_576F3C33.html | Close project or phase |  | Finalize all activities to formally complete the project or phase. | 0 days | 0 hrs | Tue 2/26/19 | Tue 2/26/19